## Prod Backlog
ID | Theme | As a | I want to | So that | Priority | Points | Status | Iteration
1 | Search | Anonymous/Registered user | Searchy by type (Sedan,SUV, Van) | I can choose a car | M | 3 | Not Started | 1
2 | Search | Anonymous/Registered user | Searchy by Keyword (Car name) | I can choose a car | H | 3 | Not Started | 1
3 | Search | Anonymous/Registered user | Searchy by Keyword (Dealer name) | I can choose a dealer | H | 3 | Not Started | 1
4 | Search | Anonymous/Registered user | Search for dealers for a zipcode | I can contact a dealer near by and based on price | M | 5 | Not Started | 2
5 | Search | Anonymous/Registered user | Search by county name | To choose dealers from same county | M | 3 | Not Started | 1
6 | Search | Anonymous/Registered user | Search by Color | To choose desired colors | L | 1 | Not Started | 2
7 | Search | Anonymous/Registered user | Search by power source | to choose hybrid/regular/electrical | L | 1 | Not Started | 2
8 | Search | Anonymous/Registered user | Search by price range | to know the cars within price range | H | 1 | Not Started | 1
9 | Search | Anonymous/Registered user | Search by transmission | to know auto/manual | M | 1 | Not Started | 2
10 | Search | Anonymous user | Save search | I can share the search | L | 3 | Not Started | 2
11 | Search | Registered user | Check the history of search | I don’t need to re-enter the same criteria | L | 3 | Not Started | 2
12 | Search | Anonymous/Registered user | Browse the vehicle details | I can get detailed info about the car | H | 3 | Not Started | 1
13 | Search | Anonymous/Registered user | Search by lease or to buy | I can get to choose one | H | 1 | Not Started | 2
14 | Registration | Anonymous user | Register manually | I can get alerts about deals | H | 3 | Not Started | 1
15 | Registration | Anonymous user | Register using FB | I don’t need to enter info manually | L | 5 | Not Started | 2
16 | Registration | Anonymous user | Register using Google | I don’t need to enter info manually | L | 5 | Not Started | 2
17 | Registration | Ford Admin | Register all dealers manually | Dealers will have the access to the app | H | 3 | Not Started | 1
18 | Test Drive | Registered user | Book a slot by my time | I can do the test drive in my schedule | M | 3 | Not Started | 2
19 | Test Drive | Registered user | Book a slot by selecting from given | I can choose an earliest | H | 3 | Not Started | 1
20 | Test Drive | Anonymous user | Register & Book a slot | I can test drive | M | 2 | Not Started | 1
21 | Test Drive | Registered user | Cancel the booking for test drive | I can re-schedule later | H | 2 | Not Started | 1
22 | Test Drive | Dealer | Update test drive slots | to allow users to choose from the latest | M | 2 | Not Started | 1
23 | Test Drive | Dealer | Remove test drive slots | to allow users to choose from the latest | M | 2 | Not Started | 1
24 | Test Drive | Dealer | Cancel the booking for test drive | User will be notified with the reason | M | 3 | Not Started | 2
25 | Test Drive | Dealer | Rescheduling the existing booking | User will be notified with the reason | M | 3 | Not Started | 2
26 | Test Drive | Dealer | Schedule a new test drive slot | user will have a test drive on a slected time | L | 2 | Not Started | 2
27 | Account Mgmt | Registered user | Update user details | I can update user name | M | 2 | Not Started | 1
28 | Account Mgmt | Registered user | Update user contact details | I can update email address/contact ph | M | 3 | Not Started | 1
29 | Account Mgmt | Registered user | delete my account | I don’t get notifications | L | 1 | Not Started | 2
30 | Account Mgmt | Registered user | Alert preferences | I can choose whatever I want. | L | 2 | Not Started | 2
31 | Inventory | Dealer | Update the inventory | Users will have updated list of cars | H | 3 | Not Started | 1
32 | Inventory | Dealer | Offer deals & discounts | to get attract customers | M | 3 | Not Started | 2
[5 empty] | Total | 83

## Sprint Backlog
ID | Theme | Tasks | Assigned To | As a | I want to | So that | Points | Status
1 | Search |  | Subbarao/Limbrit | Anonymous/Registered user | Searchy by type (Sedan,SUV, Van) | I can choose a car | 3 | Not Started
1.1 |  | Create ATC Server side
Create ATC UI side
Setup the Server side dev env
Setup the client side dev env
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create UTC and develop utility components
Create Integration test cases for Server side
Create Integration test cases for UI side
2 | Search |  | subbarao/Limbrit | Anonymous/Registered user | Searchy by Keyword (Car name) | I can choose a car | 3 | Not Started
Create ATC Server side
Create ATC UI side
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create Integration test cases for Server side
Create Integration test cases for UI side
3 | Search |  | subbarao/Limbrit | Anonymous/Registered user | Searchy by Keyword (Dealer name) | I can choose a dealer | 3 | Not Started
Create ATC Server side
Create ATC UI side
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create Integration test cases for Server side
Create Integration test cases for UI side
5 | Search |  | Sunil/Siva | Anonymous/Registered user | Search by county name | To choose dealers from same county | 3 | Not Started
8 | Search |  | Subbarao/Limbrit | Anonymous/Registered user | Search by price range | to know the cars within price range | 1 | Not Started
12 | Search |  | Sunil/Siva | Anonymous/Registered user | Browse the vehicle details | I can get detailed info about the car | 3 | Not Started
19 | Test Drive |  | Karthikeya/Ganga | Registered user | Book a slot by selecting from given | I can choose an earliest | 3 | Not Started
20 | Test Drive |  | Karthikeya/Ganga | Anonymous user | Register & Book a slot | I can test drive | 2 | Not Started
21 | Test Drive |  | Karthikeya/Ganga | Registered user | Cancel the booking for test drive | I can re-schedule later | 2 | Not Started
22 | Test Drive |  | Karthikeya/Ganga | Dealer | Update test drive slots | to allow users to choose from the latest | 2 | Not Started
23 | Test Drive |  | Sunil/Siva | Dealer | Remove test drive slots | to allow users to choose from the latest | 2 | Not Started
31 | Inventory |  | Sunil/Siva | Dealer | Update the inventory | Users will have updated list of cars | 3 | Not Started
14 | Registration |  | Ramesh/Nagaraju | Anonymous user | Register manually | I can get alerts about deals | 3 | Not Started
Create ATC Server side
Create ATC UI side
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create Integration test cases for Server side
Create Integration test cases for UI side
17 | Registration |  | Ramesh/Nagaraju | Ford Admin | Register all dealers manually | Dealers will have the access to the app | 3 | Not Started
Create ATC Server side
Create ATC UI side
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create Integration test cases for Server side
Create Integration test cases for UI side
27 | Account Mgmt |  | Ramesh/Nagaraju | Registered user | Update user details | I can update user name | 2 | Not Started
Create ATC Server side
Create ATC UI side
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create Integration test cases for Server side
Create Integration test cases for UI side
28 | Account Mgmt |  | Ramesh/Nagaraju | Registered user | Update user contact details | I can update email address/contact ph | 3 | Not Started
Create ATC Server side
Create ATC UI side
Create Domain objects
Create Unit test cases & develop Controller
Create Unit test cases & develop Service layer
Create Unit test cases for client side dev
Develop UI layout & Activity
Create Integration test cases for Server side
Create Integration test cases for UI side